SIGN-BRIDGE

A Dual-Communication Robotic Translator

Built for Indian Sign Language (ISL) · Scrap-Material Robotic Hands + AI Vision

Project Implementation Plan

Sequence · Architecture · Bill of Materials · Schedule · Risk Plan

# 1. Project Objective

Sign-Bridge is a two-way (dual) communication system that breaks down the barrier between Deaf/Hard-of-Hearing signers and hearing individuals in India, using Indian Sign Language (ISL) as the medium. It combines a scrap-material robotic hand pair, a webcam-based AI vision pipeline, and a microcontroller-driven servo system to translate:

- ISL signs → spoken/written language, for a hearing person to understand a Deaf signer.

- Spoken/written language → ISL fingerspelling and gestures, physically performed by the robotic hands, for a Deaf person to understand a hearing speaker.

Why ISL specifically changes the design: Unlike the American Sign Language (ASL) alphabet, which is almost entirely one-handed, the ISL alphabet is predominantly two-handed — most letters and numbers require both hands to shape a single sign. This means Sign-Bridge cannot be reduced to a “one hand fingerspells everything” design the way an ASL project could. A two-hand robotic system is a functional requirement for ISL fingerspelling, not just an upgrade for whole-word vocabulary.

# 2. System Architecture: The Dual Communication Loop

## 2.1 Path 1 — Human Signs → Text/Speech (Input Path)

Deaf user signs in ISL in front of a laptop webcam → MediaPipe/OpenCV vision pipeline extracts hand landmarks → a trained classifier maps the landmark pattern to an ISL letter/word → result is rendered as on-screen text and/or spoken aloud via text-to-speech for the hearing user.

## 2.2 Path 2 — Text/Speech → Robotic Hands (Output Path)

Hearing user types or speaks into a microphone → speech-to-text (if spoken) converts audio to a string → the controller breaks the string into letters/known-words → a pre-calibrated servo-angle sequence is looked up for each letter/word → Arduino drives the two scrap-material robotic hands to physically form the corresponding ISL signs in sequence.

## 2.3 Data Flow Summary

| [Deaf User] ──(Signs)──> [Webcam + MediaPipe] | ──> [Text / Speech Output] ──> [Hearing User] |
| --- | --- |
| [Deaf User] <──(Watches Hands)── [Robot Hands] | <── [Servo Sequencer] <── [Text / Speech Input] <── [Hearing User] |

# 3. Recommended Project Sequence

Build in this order. Each phase produces a working, demoable milestone before moving to the next — this avoids the common failure mode of wiring everything at once and debugging blind.

- Phase 0 — Research & ISL Reference Collection

- Phase 1 — Mechanical Design: build ONE scrap-material hand

- Phase 2 — Electronics & Wiring: 5 servos → Arduino Uno (single hand)

- Phase 3 — Output Programming: Text/Speech → single-hand ISL fingerspelling

- Phase 4 — Input Pipeline: Webcam + MediaPipe → ISL sign → Text/Speech

- Phase 5 — Scale to Second Hand: 10 servos → Arduino Mega, full two-hand ISL letters

- Phase 6 — Whole-Word / Phrase Vocabulary Layer

- Phase 7 — Integration Testing, Calibration & Troubleshooting

- Phase 8 — Final Demo Packaging

# 4. Detailed Implementation Plan

## Phase 0 — Research & ISL Reference Collection

- Collect a reference chart of the ISL manual alphabet (A–Z) and 0–9, noting which letters are one-handed vs two-handed.

- Identify 5–10 common ISL whole-word signs to target first (e.g. “hello”, “thank you”, “yes”, “no”, “help”, “water”, “food”, “family”).

- Source or plan to record a small ISL image/video dataset for training the vision classifier, since most public hand-gesture datasets (e.g. Kaggle ASL sets) are ASL-based and will not transfer directly to ISL two-handed signs.

- List locally available scrap: cereal-box cardboard, PVC/plastic bottles, drinking straws, fishing line/dental floss, an old glove.

## Phase 1 — Mechanical Design (Build One Hand First)

- Trace and cut a hand-and-forearm shape from stiff cardboard or a flattened plastic bottle.

- Cut drinking straws into knuckle-length segments and glue/tape them along each finger as joint sleeves.

- Thread strong string (fishing line or dental floss) through each straw ‘finger’, anchoring one end at the fingertip.

- Build a simple palm-back mounting plate to hold 5 servo motors, with a return spring or elastic band per finger so it relaxes when the servo releases tension.

- Reinforce high-stress points (finger base, palm-servo mounts) with extra cardboard layers or hot glue to fight the friction/tearing weak point called out for scrap builds.

## Phase 2 — Electronics & Wiring (Single Hand)

- Mount 5x SG90 micro servos in the forearm/palm housing, one per finger tendon.

- Wire servo signal pins to 5 PWM-capable pins on an Arduino Uno; wire all servo grounds to a common ground with the Arduino.

- Power the servos from a separate 5V supply (not the Arduino 5V pin) to avoid brownouts, sharing only ground with the Arduino.

- Add a breadboard/terminal block junction so wiring can be re-checked without resoldering.

## Phase 3 — Output Programming (Text/Speech → Single-Hand Signs)

- Write an Arduino sketch that maps a servo-angle set to each one-handed ISL letter/number the single hand can perform.

- Build a simple serial-controlled interface: a companion Python script on the laptop accepts typed text (or speech-to-text output) and sends the matching letter sequence to the Arduino over USB serial.

- Calibrate each servo angle manually against the physical hand, since flexible scrap joints need fine-tuning beyond theoretical angles.

## Phase 4 — Input Pipeline (Webcam → ISL → Text/Speech)

- Use a laptop webcam with Google MediaPipe Hands to extract real-time hand-landmark coordinates — this avoids building a costlier sensor glove.

- Train or fine-tune a lightweight classifier (e.g. a small scikit-learn/TensorFlow model) on the recorded ISL landmark dataset from Phase 0 to recognize target letters/words.

- Display the recognized sign as on-screen text and pass it to a text-to-speech engine (e.g. pyttsx3 or a cloud TTS API) so a hearing user gets spoken output.

## Phase 5 — Scale to Two Hands (Full ISL Alphabet Capability)

- Duplicate the Phase 1 mechanical build for a second hand (mirror-image), since most ISL letters require both hands together.

- Migrate the controller from Arduino Uno to Arduino Mega to get the 10+ PWM pins needed for 10 finger servos.

- Extend the servo-angle lookup table so each ISL letter/number is defined as a synchronized pose across both hands, not just one.

- Add a simple wrist/arm-position stage (servo or fixed bracket) if a sign requires the two hands to be positioned relative to each other, not just finger shapes.

## Phase 6 — Whole-Word / Phrase Vocabulary Layer

- Layer a small “word library” on top of fingerspelling: map common whole-word ISL signs (from Phase 0's shortlist) to their own two-hand motion sequences, since real ISL communication relies heavily on these rather than spelling everything out.

- Update the text-to-sign controller so it checks the incoming text against the word library first, and falls back to letter-by-letter fingerspelling for anything not in the library.

## Phase 7 — Integration Testing, Calibration & Troubleshooting

- Run end-to-end tests of both communication paths together with real signers/speakers if possible.

- Expect and budget time for: snapped tendon strings, cardboard joints loosening under repeated pulls, and servo-angle drift needing re-calibration.

- Log misrecognitions from the vision model and add extra training samples for the letters/words it confuses most.

## Phase 8 — Final Demo Packaging

- Add a simple enclosure/labeling so the two hands, camera, and controller box present cleanly for a demo or evaluation.

- Prepare a short live-demo script: one sentence signed by a human → spoken by the system, and one spoken sentence → signed by the robot hands.

# 5. Bill of Materials & Cost Estimate

Structure is built entirely from scrap (zero material cost). Budget is spent only on electronics. Figures below scale a single hand up to the full two-hand system.

| Component | Purpose | Cost (INR) | Cost (USD) |
| --- | --- | --- | --- |
| Micro servo motors (10x SG90) | Moves the 10 fingers across both hands | ₹1,000 – ₹1,500 | $12 – $18 |
| Microcontroller (1x Arduino Mega) | Controls all 10 motors simultaneously | ₹500 – ₹800 | $6 – $10 |
| Power supply (5V 4A adapter/battery) | Powers the power-hungry servos | ₹300 – ₹500 | $4 – $6 |
| Jumper wires & breadboard | Solder-free electronics connections | ₹200 – ₹300 | $2 – $4 |
| Webcam (existing laptop camera) | Vision input for ISL recognition | Free | Free |
| Microphone (existing laptop mic) | Speech input for text/speech path | Free | Free |
| Scrap structure (cardboard, straws, string, bottles) | Frame, finger bones, and tendons | Free | Free |
| TOTAL ESTIMATE |  | ₹2,000 – ₹3,300 | $24 – $40 |

Cost-reduction tip: Build and prove out one hand first (roughly half the electronics cost) before buying the second set of five servos — this validates the mechanical and software design before doubling the investment.

# 6. Time Estimate

Total build time: approximately 30–65 hours, typically spread across 3–6 weekends/evenings.

| Activity | Hours |
| --- | --- |
| Mechanical assembly (cardboard, straws, tendons, 10 fingers) | 10 – 15 hrs |
| Electronics & wiring (10 servos + microcontroller) | 5 – 10 hrs |
| Programming & calibration (servo angles, ISL classifier) | 10 – 25 hrs |
| Testing & troubleshooting (repairs, debugging) | 5 – 15 hrs |
| TOTAL | 30 – 65 hrs |

# 7. Suggested Week-by-Week Schedule

| Week | Focus | Milestone |
| --- | --- | --- |
| Week 1 | Phase 0 + Phase 1 (research, single-hand build) | One scrap hand physically assembled |
| Week 2 | Phase 2 + Phase 3 (wiring, output code) | Single hand fingerspells one-handed ISL letters on command |
| Week 3 | Phase 4 (vision input pipeline) | Webcam recognizes a handful of ISL signs and speaks them |
| Week 4 | Phase 5 (second hand build + Mega migration) | Both hands mounted, Mega driving all 10 servos |
| Week 5 | Phase 6 (word/phrase vocabulary layer) | Robot signs 5–10 common ISL words, not just letters |
| Week 6 | Phase 7 + Phase 8 (integration, testing, demo prep) | Full dual-communication demo ready |

# 8. Key Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Cardboard tears or bends under servo pulling force | Double-layer stress points; reinforce palm mounts; use PVC/bottle plastic for high-load joints instead of pure cardboard |
| Tendon strings snap or slip | Use non-stretch fishing line/dental floss; knot with a bead or washer stop at the fingertip anchor |
| Servos lack fine control for precise ISL hand shapes | Manually calibrate angle-per-letter tables per physical hand rather than using theoretical angles; add mechanical stops |
| ISL vision dataset is scarce compared to ASL datasets | Record a small custom dataset of the target letters/words in Phase 0 rather than relying on ASL-labeled public datasets |
| Two-handed ISL signs need hand-to-hand coordination, not just finger shapes | Add a fixed or servo-driven relative positioning stage between the two hand mounts in Phase 5 |
| Arduino Uno pin limit blocks 10-servo control | Move to Arduino Mega before wiring the second hand, as planned in Phase 5 |

# 9. Future Scope

- Expand the ISL word library from 5–10 signs toward a broader practical vocabulary.

- Replace the scrap glove/webcam setup with a lightweight flex-sensor glove for more consistent input recognition.

- Add facial-expression or head-movement capture, since ISL (like most sign languages) uses non-manual markers alongside hand shapes.

- Package the whole system into a portable kiosk form factor for use at reception desks, hospitals, or government service counters.